## Sheet1
Project Name: Dmoney web |  |  | Environment
Tester's Name : Sanzida |  |  | Reviewed By
Date Tested |  |  | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Dmoney/Tansaction | Should be clcikable of profile name | After login the Dmoney web then clcik left side menu bar of profile name but don't clickable the profile | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials | Bug | Medium | Major
2 | Dmoney/Tansaction | Dmoney logo should be clickable | When Dmoney company name or icon click and already have user list page then Dmoney logo don't any response or clickable | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials | Bug | Low | Minor
3 | Dmoney/Tansaction | Load speed | When move or clcik to another button oother function, speed very low | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials | Bug | Medium | Major
4 | Dmoney/Tansaction | email/gamil name issue | When create a user and set a gmail address start with capital letter then create a account | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials 4. Go the create user and put a gamil address starting with upper case | Bug | Medium | Minor
5 | Dmoney/Tansaction | Tansaction details search with Account | when search any transaction details in transaction search bar but don't get any search result | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials 4. Go Transaction button and don't show any search bar | Bug | Medium | Minor
6 | Dmoney/Tansaction | User info editing | when any user info want to role type edit but don't showing all roles of editing time | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials 4. Go the edit and don't get all of roles option | Bug | Medium | Major
7 | Dmoney/Payment or Deposit | In statement button can't search bar | when want to any user or account details | 1. Go to the url 2.login with gmail and password 3. then login as system user with system's credentials 4. Go the statement button and don't get any search bar | Require | Medium | Major
8 | Dmoney/Payment or Deposit | Notify of service charge | when payment amount don't show or pop/comment any service charge. If it showing as comment/popup then will be very clear for a user | 1. Go to the url 2.login with gmail and password 3. then login as system user with system's credentials 4. Go the payment option | Require | Medium | Major
9 | Dmoney/Payment or Deposit | From deposit customer A/C | Here showing A/C number of deposit time but it is better if showing Phone number or any type | 1. Go to the url 2.login with gmail and password 3. then login as system user with system's credentials 4. Go the depostie option | Require | Low | Low
10 | Dmoney/Payment or Deposit | Notify deposite max/min amount | when want to desposite amount, here max/min amount show as comment or popup any msg it will be better for a user | 1. Go to the url 2.login with gmail and password 3. then login as system user with system's credentials 4. Go the create payment option | Require | Low | Low
11 | Dmoney/Payment or Deposit | Delete any type of users | any type of user delete any users or customer. even a user can delete to admin or super-admin | 1. Go to the url 2.login with gmail and password 3. then login as admin with admin's credentials | Require | Medium | Major